## Final Cash Flow adjust Feb 24 (hidden)
NTINGA O.R. TAMBO DEVELOPMENT AGENCY SOC LTD ANNUAL BUDGET FOR THE 2023/2024 FINANCIAL YEAR
BUDGETED STATEMENT OF CASH FLOWS
Description | 2019/20 |  |  | CASH FLOWS
Rands | Audited Outcome | Adjusted Budget 2023/2024 |  | JAN 23 | FEB 24 | MARCH 24 | APRIL 24 | MAY 24 | JUNE 24 | TOTAL | December YTD 23 | YTD + Projections | Adjust budg - YTD + Projection
Revenue by Source
Fresh Farm Products - Meat and slaughter services | 10873350 | 19985298.434 |  | 1153217.1075 | 1614503.9505 | 1845147.372 | 1977740.8 | 1730523.2 | 1236088 | 9557220.43 | 10428078 | 19985298.43 | 0.004
Kei Fresh Produce Market revenue | 1571310 | 2120000 |  | 314147.5569 | 314147.5569 | 314147.5569 | 350814.2236 | 350814.2236 | 343781.8836 | 1987853.0015 | 132147 | 2120000.0015 | -0.0015
Interest earned - external investments | 385520 | 500000 |  | 15428.8333 | 15428.8333 | 15428.8333 | 15428.8333 | 15428.8333 | 15428.8333 | 92573 | 407427 | 500000 | 0
Special Projects and other conditional grants | 0 | 3846394.8743 | #REF! | 73280 | 73280 | 3290671.3043 | 73280 | 73280 | 262602.83 | 3846394.1343 | 0 | 3846394.1343 | 0.74
Transfers and Subsidies (ORTDM) | 46514585 | 49553214 |  | 3566666.6667 | 3566666.6667 | 6784057.9667 | 2345274.5667 | 2345274.5667 | 2345274.5667 | 20953215 | 28600000 | 49553215 | -1
Water Services - Debt recovery | 0 | 897023.4 |  | 0 | 0 | 0 | 0 | 0 | 897023 | 897023 |  | 897023 | 0.4
Other revenue | 1152419 | 195000 |  | 6722 | 6722 | 6722 | 6722 | 6722 | 6722 | 40332 | 154668 | 195000 | 0
Sales of Fresh Farm Products - Animals and crops | 1334445 | 5714512 |  | 283333.3333 | 283333.3333 | 283333.3333 | 1360816.5 | 1360816.5 | 1049097 | 4620730 | 1093782 | 5714512 | 0
Adjustments to biological assets | 6604567 | 2150000 | [6 empty] | 2150000 | 2150000 | 19800 | 2169800 | -19800
Gains on disposal of PPE | 4731 | 1500000 | [6 empty] | 1500000 | 1500000 |  | 1500000 | 0
Total Revenue (excluding capital transfers and contributions) | 68440927 | 86461442.7083 | #REF! | 5412795.4977 | 5874082.3408 | 12539508.3666 | 6130076.9236 | 5882859.3236 | 9806018.1136 | 45645340.5658 | 40835902 | 86481242.5658
Expenditure By Type
[15 empty] | 3694791 | 307276 | 3387515
Employee related costs | 45031065 | 41991110 |  | 3257921.3333 | 3257921.3333 | 3257921.3333 | 3257921.3333 | 3257921.3333 | 3257921.3333 | 19547528 | 22443582 | 41991110 | 0 | 19547528 | 3257921.3333
Board of Directors related costs | 800069 | 1044077.7857 |  | 261698.9 |  |  | 203654.54 |  |  | 465353.44 | 578724 | 1044077.44 | -0.3457 |  | 3695772
Depreciation & Asset Impairment | 5466038 | 4767449.592 |  | 410154.7653 | 410154.7653 | 410154.7653 | 410154.7653 | 410154.7653 | 410154.7653 | 2460928.592 | 2306521 | 4767449.592 | 0
Finance charges | 70020 | 55342.98 |  | 9223.83 | 9223.83 | 9223.83 | 9223.83 | 9223.83 | 9223.83 | 55342.98 | 114747 | 170089.98 | 114747
Operational cost | 3397771 | 32405574.1772 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 16224799 | #REF! | #REF!
Special Projects (Transfers and Grants) | 5027806.73 | 3628674.4098 |  | 1814337.2049 | 1814337.2049 |  |  |  |  | 3628674.4098 |  | 3628674.4098 | 0
Total Expenditure | 86486515 | 83892228.9447 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 41668373 | #REF! | #REF!
#REF!
Capital Expenditure |  | 2475000 |  |  | 120000 |  | 1500000 | 0 | 569159.15 | 2189159.15
[12 empty] | 1317785.5295 | #REF!
[5 empty] | 16180775.1772 |  | 2460928.592 | 410154.7653 |  |  |  | 207400

## Final Revised cash F 270224 (hidden)
NTINGA O.R. TAMBO DEVELOPMENT AGENCY SOC LTD ANNUAL BUDGET FOR THE 2023/2024 FINANCIAL YEAR
BUDGETED STATEMENT OF CASH FLOWS
Description | 2019/20 |  |  | CASH FLOWS
Rands | Audited Outcome | Adjusted Budget 2023/2024 |  | JAN 23 | FEB 24 | MARCH 24 | APRIL 24 | MAY 24 | JUNE 24 | TOTAL | December YTD 23 | YTD + Projections | Adjust budg - YTD + Projection
Revenue by Source
Fresh Farm Products - Meat and slaughter services | 10873350 | 19985298.434 |  | 1153217.1075 | 1614503.9505 | 1845147.372 | 1977740.8 | 1730523.2 | 1236088 | 9557220.43 | 10428078 | 19985298.43 | 0.004
Kei Fresh Produce Market revenue | 1571310 | 2120000 |  | 314147.5569 | 314147.5569 | 314147.5569 | 350814.2236 | 350814.2236 | 343781.8836 | 1987853.0015 | 132147 | 2120000.0015 | -0.0015
Interest earned - external investments | 385520 | 500000 |  | 15428.8333 | 15428.8333 | 15428.8333 | 15428.8333 | 15428.8333 | 15428.8333 | 92573 | 407427 | 500000 | 0
Special Projects and other conditional grants | 0 | 3846394.8743 | #REF! | 73280 | 73280 | 3290671.3043 | 73280 | 73280 | 262602.83 | 3846394.1343 | 0 | 3846394.1343 | 0.74
Transfers and Subsidies (ORTDM) | 46514585 | 49553214 |  | 3566666.6667 | 3566666.6667 | 6784057.9667 | 2345274.5667 | 2345274.5667 | 2345274.5667 | 20953215 | 28600000 | 49553215 | -1
Water Services - Debt recovery | 0 | 897023.4 |  | 0 | 0 | 0 | 0 | 0 | 897023 | 897023 |  | 897023 | 0.4
Other revenue | 1152419 | 195000 |  | 6722 | 6722 | 6722 | 6722 | 6722 | 6722 | 40332 | 154668 | 195000 | 0
Sales of Fresh Farm Products - Animals and crops | 1334445 | 5714512 |  | 283333.3333 | 283333.3333 | 283333.3333 | 1360816.5 | 1360816.5 | 1049097 | 4620730 | 1093782 | 5714512 | 0
Adjustments to biological assets | 6604567 | 2150000 | [6 empty] | 2150000 | 2150000 | 19800 | 2169800 | -19800
Gains on disposal of PPE | 4731 | 1500000 | [6 empty] | 1500000 | 1500000 |  | 1500000 | 0
Total Revenue (excluding capital transfers and contributions) | 68440927 | 86461442.7083 | #REF! | 5412795.4977 | 5874082.3408 | 12539508.3666 | 6130076.9236 | 5882859.3236 | 9806018.1136 | 45645340.5658 | 40835902 | 86481242.5658
Expenditure By Type
[15 empty] | 3694791 | 307276 | 3387515
Employee related costs | 45031065 | 41991110 |  | 3257921.3333 | 3257921.3333 | 3257921.3333 | 3257921.3333 | 3257921.3333 | 3257921.3333 | 19547528 | 22443582 | 41991110 | 0 | 19547528 | 3257921.3333
Board of Directors related costs | 800069 | 1044077.7857 |  | 261698.9 |  |  | 203654.54 |  |  | 465353.44 | 578724 | 1044077.44 | -0.3457 |  | 3695772
Depreciation & Asset Impairment | 5466038 | 4767449.592 |  | 410154.7653 | 410154.7653 | 410154.7653 | 410154.7653 | 410154.7653 | 410154.7653 | 2460928.592 | 2306521 | 4767449.592 | 0
Finance charges | 70020 | 55342.98 |  | 9223.83 | 9223.83 | 9223.83 | 9223.83 | 9223.83 | 9223.83 | 55342.98 | 114747 | 170089.98 | 114747
Operational cost | 3397771 | 32405574.1772 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 16224799 | #REF! | #REF!
Special Projects (Transfers and Grants) | 5027806.73 | 3628674.4098 |  | 1814337.2049 | 1814337.2049 |  |  |  |  | 3628674.4098 |  | 3628674.4098 | 0
Total Expenditure | 86486515 | 83892228.9447 |  | 9894261.3387 | 9956848.2537 | 12940829.6091 | 9954261.3387 | 9905554.7937 | 10115454.6971 | #REF! | 41668373 | #REF! | #REF!
Capital Expenditure |  | 2475000 |  |  | 120000 |  | 1500000 | 0 | 855000 | 2475000
[12 empty] | 1317785.5295 | #REF!
[5 empty] | 16180775.1772 |  | 2460928.592 | 410154.7653 |  |  |  | 207400

## Cover Page
NTINGA O. R. TAMBO DEVELOPMENT AGENCY SOC LTD
(A MUNICIPAL ENTITY OF THE O. R. TAMBO DISTRICT MUNICIPALITY : REGISTRATION NUMBER: 2016/272582/30)
SOC Ltd
SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN (SDBIP)
2024/25

## Midterm Report 2024-25
NTINGA O.R. TAMBO DEVELOPMENT AGENCY SOC LTD
2024/25 MIDTERM TERM PERFORMANCE REPORT (JULY- DECEMBER 2024)
COMPONENT ONE : QUARTERLY PROJECTION OF SERVICE DELIVERY TARGETS AND PERFORMANCE INDICATORS
GOAL: 1 | Enhanced and Enabled Full Value Chains (upstream and downstream) for Agricultural Produce, Markets and Abattoirs.
Strategic Objectives | Key Performance Indicators | Interventions / Critical Success Factors | Baseline 2023/24 | 2024/2025 Performance Target | Quarter 1 Performance Target | Quarter 2 Performance Target | Midterm Actual Performance (July- December 2024) | Performance Variance & Reasons | Corrective Measure | Responsible Person | Means of Verification / POE
1.1 Improve productivity and profitability of Umzikantu Abattoir by 30 June 2027 | 1.1.1 Number of livestock units slaughtered for communities, butcheries, and other meat retailers. | Improved profitability and operational efficiency Recapitalisation of the abattoir - Production and marketing of red meat (cattle, sheep, goats & pigs) carcasses and offal, locally and beyond. Strategic positioning of Meat Market to KFPM - Utilisation of abattoir for slaughtering incrementally towards full capacity. | 369 Livestock units slaughtered for communities, butcheries, and others. | 378 Livestock units slaughtered for communities, butcheries, and others. | 76 Livestock units slaughtered for communities, butcheries, and others. | 131 Livestock units slaughtered for communities, butcheries, and others. | Over Achieved: 321.42 Livestock units slaughtered for communities, butcheries, and others. | There is a positive variance of 114.42 Livestock units slaughtered for communities butcheries and other | Not Applicable | HOD: Trading Enterprises | Batch Control Document
| 1.1.2. Number of livestock units slaughtered for sale, towards abattoir full capacity. |  | 1142 Livestock units slaughtered for sale, towards abattoir full capacity. | 1764 Livestock units slaughtered for sale, towards abattoir full capacity. | 441 Livestock units slaughtered for sale, towards abattoir full capacity. | 442 Livestock units slaughtered for sale, towards abattoir full capacity. | Partially Achieved: 648.83 Livestock units slaughtered for sale, towards abattoir full capacity | There is a negative variance of 234.17 Livestock units slaughtered for sale, towards abattoir full capacity. | The appointment of the panel of livestock suppliers which was concluded in December 2024 is designed to address the gap of lack of supplies for both Sheep and Pigs. | HOD: Trading Enterprises | Batch Control Document
| 1.1.3 Revenue generated from meat sales and slaughter fees for Abattoir and Meat Market |  | R19 985 298 Revenue generated from meat sales and slaughter fees. | R29 835 879 Revenue generated from meat sales and slaughter fees for abattoir & Meat Market | R7 542 266 Revenue generated from meat sales and slaughter fees for abattoir & Meat Market | R7 320 116 Revenue generated from meat sales and slaughter fees for abattoir & Meat Market | Partially Achieved: R11 208 584.77 Revenue generated from meat sales and slaughter fees for abattoir & Meat Market | There is a negative variance of R3 653 797.23 Revenue generated from meat sales and slaughter fees for abattoir & Meat Market | The appointment of the panel of livestock suppliers which was concluded in December 2024 is designed to address the gap of lack of supplies for both Sheep and Pigs. | HOD: Trading Enterprises | Financial Report | R1 777 955 Revenue generated from meat sales and slaughter fees. | R2 222 444 Revenue generated from meat sales and slaughter fees.
1.2 Improve functionality and viability of Kei Fresh Produce Market (KFPM) by initially focusing and targeting linkages of fruits, vegetables and meat industry supply chains by 30 June 2027. | 1.2.1 Tonnage of agricultural produce sold by Market Agents | Mapping out local suppliers and ensuring Improved profitability and operational efficiency on all trading enterprises. Recapitalisation of the Market infrastructure and facilities. - Establishment and recruitment of market agents Encourage aggressive marketing and sale of fresh produce (fruit and vegetables) locally and beyond by Market Agents. | 3341 Tons of Agricultural Produce sold by Market Agents. | 3777 tons of Agricultural Produce sold by Market Agent | 328.47 tons of Agricultural Produce sold by Market Agents. | 1321.94 tons of Agricultural Produce sold by Market Agents. | Partially Achieved: 301, 83 tons of Agriculatural Produce sold by Market Agent | A negative variance of 1348.58 tons of Agricultural Produce sold by Market Agents. The Market Agent has sold products with lower value and tonnage, that includes cabbage, spinach and yellow maize. The Agent had difficulty in sourcing higher value fruits and vegetables especially potatoes, onions and bananas, and that has contributed towards poor performance especially in October and November months. | Engagements with local farmers throughout the O.R. Tambo District and Alfred Nzo District were made with the aim of sourcing produce and coordinating production, this initiative has started to yield results even though farmers had only brought Yellow Maize, Cabbage and Spinach. Ntinga has assisted the Market Agent in ensuring that there is product availability at all times by visiting farmers and to source stock from the local and commercial farmers as well as the neighbouring markets, the first batch of Potatoes, Onion and Bananas has arrived on 30 November and will be sold from the 2nd of December, this initiative has assisted in increasing tonnage as well as revenue from 5% commission in the month of December. | HOD: Trading Enterprises | Freshmark System monthly reports.
| 1.2.2 Revenue generated from 5% commission of agricultural produce sold |  | R1,210 000 Revenue generated from 5% commission of agricultural produce sold. | R1 035 000 Revenue generated from 5% commission of agricultural produce sold. | R90 000 Revenue generated from 5% commission of agricultural produce sold. | R362 250 Revenue generated from 5% commission of agricultural produce sold. | Partially Achieved: R72 378.63 Revenue generated from 5% commission of agricultural produce sold. | A negative variance of R379, 871.37 Revenue generated from 5% commission of agricultural Produce sold by Market Agents. The Market Agent has sold products with lower value and tonnage, that includes cabbage, spinach and yellow maize. The Agent had difficulty in sourcing higher value fruits and vegetables especially potatoes, onions and bananas, and that has contributed towards poor performance in October and November months. | Engagements with local farmers throughout the O.R. Tambo District and Alfred Nzo District were made with the aim of sourcing produce and coordinating production, this initiative has started to yield results even though farmers had only brought Yellow Maize, Cabbage and Spinach. Ntinga has assisted the Market Agent in ensuring that there is product availability at all times by visiting farmers and to source stock from the local and commercial farmers as well as the neighbouring markets, the first batch of Potatoes, Onion and Bananas has arrived on 30 November and will be sold from the 2nd of December, this initiative has assisted in increasing tonnage as well as revenue from 5% commission in the month of December. | HOD: Trading Enterprises | Freshmark System monthly reports.
| 1.2.3 Full utilisation of KFPM floor space for revenue generation |  | Two additional competitive market agent secured. | Two Additional competitive Market Agents secured who can fill floor space. | No target set for this quarter | Two Additional competitive Market Agent secured who can fill floor space. | Not Achieved: 0 Additional competitive Market Agent secured who can fill floor space. | In Quarter 1 the entity has advertised for two (2) additional Market Agents (1 Local Market Agent and 1 Commercial Market Agent) with the aim that they will be starting trading in Quarter 2, there were no responses received from the advertisement. | The entity have started with the head hunting of market agents and only one BEE Market Agent have shown interest and currently busy with APAC compulsory e-learning modules by the 30 June 2025 | HOD: Trading Enterprises | Freshmark System monthly reports.
1.3 Utilise Adam Kok Farms as a primary production hub for agricultural produce by 30 June 2027. | 1.3.1 Number of cattle produced, sourced, and supplied to Umzikantu Abattoir. | Availability and sustainability of feedstock and markets. Improved profitability and operational efficiency. Recapitalisation of AKF Purchase cattle ready for slaughter. Cull, and condition/fatten old cows. Exchanged heifers and condition/fatten cattle from exchange. Implement Standard breeding practices | 914 Cattle produced, sourced, and supplied to Umzikantu Abattoir. | 1260 Cattle produced, sourced, and supplied to Umzikantu Abattoir. | 315 cattle produced, sourced and supplied to Umzikantu abattoir. | 320 cattle produced, sourced and supplied to Umzikantu abattoir. | Partially achieved: 550 cattle supplied to Umzikantu Abattoir: 64 transferred from Adam Kok Farms and 486 sourced from auctions | There is a negative variance of 85 cattle. This is because, in Quarter 1 there was a shortage of slaughter sheep that resulted to poor product mix and that caused low beef sales. | The entity has already appointed a panel for livestock suppliers including all species slaughtered at Umzikantu in December 2024. | HOD: Trading Enterprises | Transfer notes, Financial Reports
| 1.3.3 Number of hectares utilised for animal feed |  | 46 ha utilised for crop production (40ha maize, 4ha cabbage and 2ha butternut | 20 ha utilised for maize production | Procurement of inputs for 20 ha of maize | Land preparation, planting, topdressing, Sprayng (weed control, pest and disease control ) | Achieved: The operations were completed by the contracted service provider as a measure to mitigate cashflow problems experienced by the entity. The service provider signed an agreement to provide 4 tons of maize per Ha from the 20 ha. | None | Not Applicable | HOD: Trading Enterprises | Production plan, procurement vouchers, tractor log sheets, GPS Coordinates
| 1.3.4 No of feasibility studies conducted for high value crops | Availability of land and capital for inputs, infrastructure and equipment | New Target | 1 feasibility study on high value crops conducted. | No target set for this quarter | 1 feasibility study on high value crops conducted. | Not achieved: No feasibility study conducted on high value crops. | There is a negative variance of 1 feasibility study. During the expression of interest window period the production of cannabis was included. The proposals are at evaluation stage | The adjudication of proposals is set for 2024/25 Quarter 3. | HOD: Trading Enterprises | Feasibility study report
| 1.3.5. Number of Feedlots established as source of supply to Umzikantu Abattoir | Availability of funds and land | New Target | One feedlot establishment facilitated | Identifying key stakeholders on establishment of a feedlot | Facilitation of meeting with key stakeholder on establishment of feedlot | Achieved: Stakeholders were identified through the expression of interest and the SCM office facilitated the meetings for the signing of the Lease agreement with the partner to establish the feedlot at Adam Kok farms and the agreement was signed. | None | Not Applicable | HOD: Trading Enterprises | New feedlot
1.4. Coordinate livestock improvement interventions to enhance regional supply of quality stock to Umzikantu Abattoir | 1.4.1. No of bulls loaned to communities to improve quality stock | Availability of stock for genetic improvement. Increased number of branded animals from community supplied to the Abattoir . | 8 bulls loaned to communities | 4 bulls loaned to communities | No target set for this quarter | 4 bulls loaned to communities. | Not achieved: There are no bulls loaned for the period under review. | During the evaluation of applications it was noticed that most applications were from the farmers who previously benefited from the programme and from 1 local municipality | The window of application has been extended to 20 January 2025. The target is deferred to 2024/25 Quarter 3. | HOD: Trading Enterprises | Signed loan agreements
| 1.4.2. No of heifers exchanged with community cattle |  | 50 heifers exchanged with community cattle | 30 heifers exchanged with community cattle | No target set for this quarter | 30 Heifers exchanged to communities. | Not achieved: There are no heifers exchanged | During the evaluation of applications it was noticed that most applications were from the farmers who previously benefited from the programme. | The window of application has been extended to 20 January 2025. The target is deferred to 2024/25 Quarter 3 | HOD: Trading Enterprises | Signed registers
| 1.4.3. No of farmers assisted with brand mark certificate applications |  | 200 farmers assisted with brand mark certificate applications | 200 farmers assisted with brand mark certificate applications | 50 farmers assisted with brand mark certificate applications. | 75 farmers assisted with brand mark certificate applications | Over achieved: 247 farmers assisted with brand mark certificates | There is a positive variance of 122 farmers. Farmers apply as and when they can afford the fee. | Not Applicable | HOD: Trading Enterprises | List of farmers / copies of applications.
| 1.4.4. No of animal identification campaigns organised |  | 8 animal identification campaigns organised | 5 animal identification campaigns organised | 1 animal identification campaign organised | 2 animal identification campaigns organised | Achieved: 3 animal identification campaigns organised. | None | Not Applicable | HOD: Trading Enterprises | Attendance registers
GOAL: 2 | Diversified Partnerships that Promote Inclusive Socio-economic Development and Growth.
Strategic Objectives | Key Performance Indicators | Interventions / Critical Success Factors | Baseline 2023/24 Perforamance Target | 2024/25 Performance Target | Quarter 1 Performance Target | Quarter 2 Performance Target | Midterm Actual Performance (July- December 2024) | Performance Variance & Reasons | Corrective Measure | Responsible Person | Means of Verification / POE
2.1 Optimize linkages of meat industry value chain that enhance functionality of Umzikantu Abattoir by 30 June 2027. | 2.1.1 Number of signed and implemented off-take agreements for sale of meat from Umzikantu Abattoir. | 5 Off-take agreement for sale of meat from Umzikantu Abattoir signed and implemented | 5 Off-take agreement for sale of meat from Umzikantu Abattoir signed and implemented. | 4 Off-take agreements for sale of meat from Umzikantu Abattoir signed and implemented. | 1 Off-take agreement for sale of meat from Umzikantu Abattoir signed and implemented. | 1 Off-take agreement for sale of meat from Umzikantu Abattoir signed and implemented. | Achieved: 2 Offtake agreements Signed and implemented | None | Not Applicable | HOD: Trading Enterprises | 5 signed Offtake agreements
2.2 Optimize linkages of fruit and vegetable industry value chain in support of Kei Fresh Produce Market by 30 June 2027 | 2.2.1 Number of signed and implemented partnership agreements that enhance functionality of Kei Fresh Produce Market. | 1 Partnership agreement that enhance functionality of Kei Fresh Produce Market signed and implemented. | 1 Partnership agreement that enhance functionality of Kei Fresh Produce Market signed and implemented. | 1 Partnership agreement that enhances functionality of Kei Fresh Produce Market signed and implemented. | 1 meeting set in preparation for the partnership agreement. | 1 meeting set in preparation for the partnership agreement. | Partially Achieved: One (1) meeting set in preparation for the partnership agreement | The entity has not yet proceeded with meetings in preparation for the partnership agreements as the expression of interest publication closed only on 07 November 2024. | Once the proposals have gone through all SCM Bid processes and the companies that have showed interest in working with KFPM were identified the meetings will be scheduled before 31 March 2025 | HOD: Trading Enterprises | Attendance Register, Minutes of (Q1). Signed Partnership Agreement with KFPM.(Q3). Implementation progress report.(Q4)
| 2.2.2 Number of signed and implemented off-take agreements with local farmers to supply KFPM with agricultural produce. | Three (3) Off-take agreements signed and implemented with local non-commercial farmers to supply KFPM with agricultural produce. | 3 off-take agreements signed and implemented with local farmers to supply KFPM with agricultural produce. | 5 off-take agreements signed and implemented with local farmers to supply KFPM with agricultural produce. | 1 off-take agreement signed and implemented with local farmers to supply KFPM with agricultural produce. | 2 off-take agreements signed and implemented with local farmers to supply KFPM with agricultural produce. | Over Achieved: 7 off-take agreements signed and implemented with local farmers to supply KFPM with agricultural produce. | Positive variance of 4 off-take agreements. Since Eyoluntu market agent has started to operate at KFPM, more farmers are seeking an agreement with the Agent in order for their produce to have access to market, hence an over achievement. | Not Applicable | HOD: Trading Enterprises | 3 signed Off-take agreements
2.3 Optimize linkages of a rapid livestock production industry value chain that enhance functionality of Adam Kok Farm by 30 June 2027 | 2.3.1 Number of signed and implemented partnership agreements that enhance functionality of Adam Kok Farms. | 1 Partnership agreement signed with potential partner to enhance functionality of Adam Kok farms Establishment of a centre of excellence at the farms. Rapid production programmes to enhance heifers and bull production. Establishment of farmers incubation programme. | 2 partnerships agreements signed and implemented with potential partners to produce stock and supply Adam Kok with produce and market. | 1 partnership agreement signed and implemented with potential partner for full utilisation of the farm. | No target set for this quarter | 1 partnership agreement signed and implemented with potential partner for full utilisation of the farm. | Over Achieved: 3 partnership agreements signed and being implemented with potential partners. | There is a positive variance of 2. This is as a result of delayed signing of agreements in the last financial year. | Not Applicable | HOD: Trading Enterprises | Attendance registers Signed partnership
|  |  | New Target | One Farmers' Incubation programme established at Adam Kok Farms. | A strategic partnership agreement with ECRDA, in support of the programme, concluded by 30 Septermber 2024. | No target set for this quarter | Not Achieved:A strategic partnership agreement with ECRDA, in support of the programme has not been concluded by 30 Septermber 2024. | The strategic partnership agreement with ECDRA has not been concluded due to the policy of ECRDA stating that there must be one incubator and the prioritised site being Magwa. | Management has issued a call for expression of interest and proposals have been received. An agreement with an appropiate partner will be signed and concluded the 31 March 2025 | HOD: Trading Enterprises | Register of participating farmers
2.4. Prioritised Sector development plans implemented by June 2025 | 2.4.1 Number of agricultural projects implemented. | *Concessions to bilateral negotiation meetings with targeted participants. *Collaboration with municipalities. *Segmentation of prioritised commodities per local municipality based on their natural endowments. * Facilitate grading and upscaling of locally produced products. *Collaborate with knowledge institutions such as University of Pretoria and Technology Innovation Agency (TIA) | 1 mechanisation Centre Established | 5 project proposals developed. | Horticulture (Vegetable and Fruit) Production Project proposal developed. | No target set for this quarter | Over Achieved: A horticulture production project proposal developed and submitted to DRDAR and Detailed Business Plan on the KFPM Packhouse submitted developed. | 1 more proposal in the form of business plan on the Fresh Produce Packhouse Developed, reason being the delayed process of planning around the packhouse. | Not Applicable | Manager: PMO | Muliti-stakeholder partnership agreement, Horticulture Production Land Map, Contract with farmers, submitted funding/finance applications .
[5 empty] | No target set for this quarter | Red Meat Production project proposal developed. | Achieved: Red Meat Production project proposal developed and submitted to ECDC. | None | Not Applicable
[5 empty] | Food Innovation and Technology Station project proposal developed. | Project Implementation Plan developed. | Partially Achieved: Proposal developed for presentation to Stakeholders on 19 July 2024. Project Implementation plan not developed. | TIA (Technology Innovation Agency) the main targeted partner could not attend two proposed sessions to discuss the issue of funding for planning and implementation of the project | Management has agreed to pursue another physical meeting with TIA (technlogy innovation agency) the meeting will be arrange before end January 2025 | Manager: PMO | Muliti-stakeholder partnership agreement, Contract with farmers, Survey Report, submitted funding/finance applications .
2.5 Resource and funding provisioning partnerships in support of prioritised programmes and projects are established by 30 June 2025 | 2.5.1 Number of resource and funding partnerships in support of prioritised sectors established. | * Appropriate and relevant networks * Fundraising and resource mobilisation resources. * Signed partnership agreements *Relevant budget with targeted Strategic partner. | 3 resource and funding partnerships with government and parastatals established. | 3 resource mobilisation and funding partnerships established | 1 resource mobilisation and funding partnership established | No target set for this quarter | Over Achieved: 1 funding partnership with ECDC, 3 funding agreements with Services Seta, and 1 funding agreement with Sacta Levy | 4 more formalised funding partnerships were concluded in writing, reason being positive response to negotiations held with Services Seta and Sacta Levy in the last Financial Year. | Not Applicable | Manager: PMO | Correspondence, attandance registers and partnership agreements
2.6 Catalytic projects geared towards stimulating local economic development implemented by June 2027. | 2.6.1 Number of catalytic projects fully implemented | * Concepts and plans approved by the parent municipality. * Collaborations and partnerships | New Target | 1 catalytic project on renewable energy implemented. | Renewable energy project poposal developed. | No target set for this quarter | Achieved: Proposal Developed providing a framework for proposals solicited through the 2024/25 first call for expression of Interest. | None | Not Applicable | Manager: PMO | Renewable energy project proposal
|  |  | New Target | 1 catalytic project on digital infrastructure implemented. | No target set for this quarter | Digital infrastructure project proposal developed. | Achieved: Digital infrastructure project proposal developed. | None | Not Applicable | Manager: PMO | Digital infrastructure project proposal
GOAL 3 | Promoted Trade and Investment Opportunities in the District
Strategic Objectives | Key Performance Indicators | Interventions / Critical Success Factors | Baseline 2023/34 Performance Target | 2024/25 Performance Target | Quarter 1 Performance Target | Quarter 2 Performance Target | Midterm Actual Performance (July- December 2024) | Performance Variance & Reasons | Corrective Measure | Responsible Person | Means of Verification / POE
3.1 Investment promoted by 30 June 2027. | 3.1.1 Number of investments into the district attracted. | * Sector Planning capacity, Co-operation of stakeholders. *National and provincial investment and trade promotion agencies, e.g. InvestSa and ECDC’s One Stop Shop *Collaboration with local municipalities *Implementation of catalytic projects. | 2 Number of infrastructure investments attracted into district tourism sites. | 2 investments attracted into the district. | No target set for this quarter | No target set for this quarter | No target set for this period | None | Not Applicable | Manager: OCEO | Trade and Investment Promotion Report
3.2. Trade development by 30 June 2027. | 3.2.1 Total rand value of goods and services facilitated by Ntinga in trade promotion. | * Database of producers and suppliers. * Identification of targeted commodoties. * Multi-stakeholder collaboration. | R50 million alue of traded oods and serices facilitated | R50 million value of goods and services facilitated by Ntinga in trade promotion. | No target set for this quarter | R10 Million value of goods and services facilitated by Ntinga in trade promotion. | Over Achieved: A rand value of R19 641 131.56 has been achieved in trading with goods and services through the KFPM, Umzikantu Red Meat Abattoir and the Sacta Levy-Ntinga Collaboration project. | The set target has been exceeded by 9 641 131.56 reason being the allocation of Sacta Levy soft loans to local farmer during the period under review. | Not Applicable | Manager: PMO | Trade and Investment Promotion Report
3.3. A five-year Supplier Development programme is developed and implemented by 30 June 2027. | 3.3.1 Number of enterprises supported | * Active suppliers * Strategic partnerships | New Target | 90 Enterprises Supported. | 22 enterprises supported. | 22 enterprises supported. | Over Achieved: 60 enterprises were supported in the 1st quarter and 537 enterprises supported in the 2nd quarter. | 553 more enterprises were supported, reason being the delayed funding response by Sacta Levy and the opportunity to submit Pesi applications to DRDAR and DALLRD. | Not Applicable | Manager: PMO | Quarterly Enterprise Development Report
GOAL 4 | Dynamic, Capable and Sustainable State-Owned Company
Strategic Objectives | Key Performance Indicators | Interventions / Critical Success Factors | Baseline 2023/24 Performance Target | 2024/25 Performance Target | Quarter 1 Performance Target | Quarter 2 Performance Target | Midterm Actual Performance (July- December 2024) | Performance Variance & Reasons | Corrective Measure | Responsible Person | Means of Verification / POE
4.1 Ensure Business Processes, Tools and Systems that support implementation of the Strategy and continued viability of the organisation by 30 June 2027. | 4.1.1 Comply with municipality reporting regulation | Accurate and complete financial records and PoE. Integrated system | 100% adherence with municipality reporting - Monthly and Quaterly report | Compliance Reports :Finance Reports (S87 & S89) ; SCM Report Paragraph 6 submitted to the Parent Municipality. | 2023/24 Quarter 4 Compliance Reports :Finance Reports (S87 & S89) ; SCM Report Paragraph 6 submitted to the Parent Municipality. | 2024/25 Quarter 1 Compliance Reports :Finance Reports (S87 & S89) ; SCM Report Paragraph 6 submitted to the Parent Municipality. | Achieved: 2023/24 4th Quarter and 2024/25 1st Quarter Compliance reports: Finance Reports(S87 & S89); SCM Report Paragraph 6 were submitted to the Parent Municipality | None | Not Applicable | CFO | *BTO Monthly Reports *Quarterly Performance Reports (Section 87, 89 , * Paragraph 6 and 36 of SCM). * Proof of submission to the Parent Municipality
|  |  |  | Facilitate reviewal and approval of policies | List of Policies to be reviewed coordinated by the 30 September 2024 . | Policy workshop conducted and policies approved by the Board on the 31 December 2024. | Achieved :1. List of policies to be reviewed coordinated by 30 September 2024 2. Policy Workshop conducted by 31 December 2024 | None | Not Applicable | HOD: Corporate Services | *Policy Review Workshop *reviewed and Approved Policies by the Board * 2024/25 updated policy register.
| 4.1.2 Value of procurement done with local suppliers (Eastern Cape). | Supplier data base registration and support | 60% value of procurement done with local Suppliers (Eastern Cape) | 60% value of procurement done with Local Supplier (Eastern Cape). | 60% value of procurement done with local Suppliers (Eastern Cape) | 60% value of procurement done with local Suppliers (Eastern Cape) | Over Achieved: 80.5% procurement done with local suppliers (Eastern Cape) | 20.5% positive variance is attributed to the SCM Unit providing feedback to service providers on their unsuccessful quotations. This has seen a marked improvement from supplier responses especially in the range of (R 2000 to R199,000) |  | CFO | Finance Supplier Report
Not Applicable
| 4.1.3 % of suppliers paid within 30 days | · Collection of due revenue. Proper Cashflow Management. | 100% of suppliers paid within 30 days from date of invoice. | 100% of suppliers paid within 30 days from date of invoice. | 100% of suppliers paid within 30 days from date of invoice. | 100% of suppliers paid within 30 days from date of invoice. | Not Achieved: 57% of invioices due were not paid within 30 days. | Due to cashflow challenges the Entity has been unable to pay invoices within 30 days. | The Entity is currently looking at alternative revenue generation streams as part a financial recovery to improve cashflow. | CFO | Finance ageing Report.
| 4.1.4 Clean administration and Improve Audit outcome | Accurate financial record and PoE Timely scheduled governance meeting. | Unqualified audit outcome | Clean audit opinion | No target set for this quarter | Clean audit opinion | Achieved: Agency received an Unqualified audit outcome | None | Not Applicable | CFO | Audit Report
4.2 Create unit of skills and competences that deliver Ntinga strategic objectives. | 4.2.1 % alignment of organisational structure to strategy. | Organisational structure review | 100% alignment of organisational structure to strategy. | 100% alignment of organisational structure to strategy by 30 June 2025 | 1. Approved 2024/2025 Organogram by the Board. 2. Job Evaluation committee appointed by 30 September 2024 | Job evaluation results presented to the committee by 31 December 2024 | Partially Achieved: Job evaluation committee was appointed by the 30 September 2024. | Organogram was not approved and Job evaluation results were not presented to the committee by 31 December 2024 because there were SCM delays in awarding the bid to the successful bidder. | Organogram will be approved after the job evaluation has been fully conducted with positions graded. The whole exercise will be completed during the fourth quarter of 2024/25 financial year. | HOD: Corporate Services | Signed JDs, appointment letters for evaluation committee,attendance registers and proof of submission to board committees.
| 4.2.2 % Improvement on retention of critical skills. | Improved retention of critical skills. | Improve retention of critical skills to 95%. | Improve retention of critical skills to 95% by 30 June 2025 | 1. Four (4) training programmes coordinated by 30 September 2024 2. Database for SETA accredited training providers coordinated by 30 September 2024 | Monitor the progress of all Approved bursaries by 31 December 2024 | Achieved1. Training coordination was done. 2. Database for SETA Accredited training providers has been developed. 3. Progress on approved bursaries is monitored. | None | Not Applicable | HOD: Corporate Services | * Quarterly: Training Report * Approved Annual Training Plan,
| 4.2.3 Percentage implementation of the ICT Master Systems Plan. | Funding of projects identified in the ICT Master Systems Plan | 80% Implementation of the ICT Master Systems Plan. | 80% Implementation of the ICT Master Systems Plan by 30 June 2025 | 1. Anti-virus software renewed. 2. Sage Evolution software renewed 3. Abaserve software renewed by 30 September 2024 | 1. Sage VIP software renewed by 31 December 2024 | Achieved :Anti-virus, Sage Evolution, Abaserve and Sage VIP softwares renewed | None | Not Applicable | HOD: Corporate Services | Renewal payment invoices and memo Project Completion certificate Implementation Report
4.3 Continuously improve internal and external reputation and image of the institution by 30 Jun 2027 | 4.3.1 Number of corporate branding initiatives implemented. | Well known corporate brand. | 4 Corporate branding initiatives implemented. | 4 Corporate branding initiatives implemented. | 1 Corporate branding initiative implemented. | 1 Corporate branding initiative implemented. | Achieved: 2 Corporate Branding initiatives implemented | None | Not Applicable | Manager: OCEO | Signed report on corporate branding initiatives
4.4 Operational resilience: ensure that your business processes are documented, business process must be aligned to your business by 30 June 2027 “ Improve business continuity to 95% reliability. | 4.4.1 Business processes and systems documented. | Revised and reviewed business processes for the entity | Revised and reviewed business processes for the entity | Develop,Revised and review business processes for the entity 1- Finance & SCM - revise & review 7- Trading Enterprises- revise & review 2- Corporate Services- Review | Develop,Revised and review business processes for the entity 1- Finance & SCM - revise & review 7- Trading Enterprises- revise & review (3 Abattoir, 3 KFPM and 1 Adam Kok Farms) 2- Corporate Services- Review (Recruitment and Leave) by 30 September 2024 | No target set for this quarter | Achieved : 1- Finance & SCM - revise & review 7- Trading Enterprises- revise & review (3 Abattoir, 3 KFPM and 1 Adam Kok Farms) 2- Corporate Services- Review (Recruitment and Leave) by 30 September 2024 | None | Not Applicable | CFO HOD: Corporate Services HOD: Trading Enterprises | Q1- 1 SOP Developed. Q2- Revised and reviewed business processes for the entity.
| 4.4.2 % of server availability based on operating hours | Entity business processes aligned | 95% server availability based on operating hours. | 95% server availability based on operating hours by 30 June 2025 | 95% server availability based on operating hours for this quarter by 30 September 2024 | 95% server availability based on operating hours for this quarter by 31 December 2024 | Achieved : 95% Server available during operating hours. | None | Not Applicable | HOD: Corporate Services | Backup Reports
4.5 Full compliance to governance, legislative and regulatory framework | 4.5.1 100% Compliance to all governance, legislative and regulatory framework. | Annual review of strategic plan by 31 May | Annual review of strategic plan by 31 May. | Annual review of strategic plan by 31 May 2025 | No Target Set for this Quarter | No target set for this quarter | No target set for this period | None | Not Applicable | Manager: OCEO | Reviewed and signed Strategic Plan
|  | Periodic Performance Reporting | 100% performance reporting | 100% performance reporting | 2023/24 4th Quarter Performance Report submitted to the Board and to the Parent Municipality | 2024/25 1st Quarter Performance Report submitted to the Board and to the Parent Municipality | Achieved: 2023/24 4th Quarter and 2024/25 1st Quarter Perfomance reports were submitted to the Board and Parent Municipality | None | Not Applicable | Manager: OCEO | * Proof of Submission to the Board and Parent Municipality. * Performance Reports: Q1- 4th Quarter Performance Report Q2- 1st Quarter Report Q3- 2nd Quarter Report - Midterm Report Q4- 3rd Quarter report * Board Minutes
[5 empty] | 2023/24 Draft Annual Performance Report submitted to the Board, Parent Municipality and AGSA | Draft Annual report submitted to ORTDM and Board by 31 December 2024 | Achieved: 2023/24 Draft Annual Report was submitted to the Board, Parent Municipality and AGSA and Draft Annual Report was submitted to ORTDM and Board by 31 December 2024 | None | Not Applicable | Manager: OCEO/CS | Proof of Submission to the Board, Parent Municipality and to AGSA- (Only Annual Performnce Report) * Board Minutes
|  | Governance, legislation and regulatory compliance checklists | 100% planning and execution of planned Board and Committee meetings, for the year | 100% planning and execution of planned Board and Committee meetings for the year | One (1) Board and 3 Committee Meetings organised. | One (1) Board and 4 Committee Meetings organised. | Over Achieved: 3 Board Meetings, 3 ARC Meetings, 2 SDIC, 2 HRRC , 1 SEC and 3 UIFW Adhoc Meetings | 3 Adhoc UIFW Meetings as established by the Board to discuss the UIFW report and provide recommendations and 1 Extra Board Meeting (to discuss the recruitment process for Head: Trading Enterprises) | Not Applicable | Company Secretary | Agenda and Minutes of Meetings.
|  | Governance, legislation and regulatory Compliance Checklists | 100% compliance to all governance, legislative and regulatory framework in line with the compliance Universe. | 100% compliance to all governance, legislative and regulatory framework in line with the compliance Universe | Compliance report submitted to the SEC Chairperson. | Compliance report presented at the SEC meeting. | Achieved: two compliance reports submitted. | None | Not Applicable | Company Secretary | Compliance Report Compliance Audit
|  | Up to the date Risk Register Risk Management oversight | 2024/25 Risk assessment and reporting conducted. | 2024/25 Risk assessment and reporting conducted. | 2024/25 Risk assessment conducted | No target set for this quarter | Achieved: Risk Assessment was conducted in July 2024 | None | Not Applicable | Manager: OCEO | 2024/ 25 Updated Risk Register
[5 empty] | 1 Risk Management Report submitted to the Audit Committee | 1Risk Management Report submitted to the Audit Committee | Achieved: quarterly reports were submitted to the Audit Committee | None | Not Applicable | Manager: OCEO | Risk Management Reports submitted to the Audit & Risk Committee

## Cash flow Summary (hidden)
NTINGA O.R. TAMBO DEVELOPMENT AGENCY SOC LTD ANNUAL BUDGET FOR THE 2024/2025 FINANCIAL YEAR
BUDGETED STATEMENT OF CASH FLOWS
Description |  | CASH FLOWS
Rands | Budget 2024/2025 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | Total | Variance
Revenue by Source
Fresh Farm Products - Meat and slaughter services | 29835879.1304 | 2754254.1067 | 2513421.9328 | 2274589.7588 | 2759814.9733 | 2518982.7994 | 2041318.4516 | 2754254.1067 | 2394005.8458 | 2394005.8458 | 2507737.8261 | 2507737.8261 | 2415755.6591 | 29835879.1322 | -0.0017391
Kei Fresh Produce Market revenue | 2275400 | 111533.3333 | 117533.33 | 122533.33 | 184533.33 | 209533.33 | 281583.33 | 217566.6633 | 214233.33 | 269816.66 | 177733.33 | 177733.33 | 191066.71 | 2275400.0067 | -0.0066667
Interest earned - external investments | 525000 | 43750 | 43750 | 43750 | 43750 | 43750 | 43750 | 43750 | 43750 | 43750 | 43750 | 43750 | 43750 | 525000 | 0
Special Projects and other conditional grants | 0 | [12 empty] | 0 | 0
Transfers and Subsidies (ORTDM) | 49553215 | 5063824.116 | 5063824.116 | 5063824.116 | 3436174.266 | 6872348.532 | 3436174.266 | 3436174.266 | 3436174.266 | 3436174.266 | 3436174.266 | 3436174.266 | 3436174.266 | 49553215.008 | -0.008 |  | 1627649.8473
Water Services - Debt recovery | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 |  | 0
Other revenue | 204750 | 17062.5 | 17062.5 | 17062.5 | 17062.5 | 17062.5 | 17062.5 | 17062.5 | 17062.5 | 17062.5 | 17062.5 | 17062.5 | 17062.5 | 204750 | 0
Rental Income from the Farm | 250000 | [5 empty] | 250000 | [6 empty] | 250000 | 0
Adjustments to biological assets | 3685334.4304 | [11 empty] | 3685334 | 3685334 | 0.43045
Gains on disposal of PPE | 0 | [13 empty] | 0
Total Revenue (excluding capital transfers and contributions) | 86329578.5609 | 7990424.056 | 7755591.8788 | 7521759.7048 | 6441335.0693 | 9661677.1614 | 6069888.5476 | 6468807.536 | 6105225.9418 | 6160809.2718 | 6182457.9221 | 6182457.9221 | 9789143.1351 | 86329578.1468 | 0.41404
Expenditure By Type
Employee related costs | 44670265.458 | 3583670.349 | 3583670.3429 | 3589175.3429 | 3583670.3429 | 5244386.3429 | 3583670.3429 | 3583670.3429 | 3583670.3429 | 3583670.3429 | 3583670.3429 | 3583670.3429 | 3583670.3429 | 44670265.1206 | 0.33738
Board of Directors Allowances | 1264689.017 | 316172.2542 |  |  |  | 316172.2542 |  |  | 316172.2542 |  |  | 316172.2542 |  | 1264689.017 | 0
Board of Directors Travelling, Accommodation & other | 80000 | 20000 |  |  | 20000 |  |  | 20000 |  |  | 20000 |  |  | 80000 | 0
Depreciation | 4007370.0493 | [12 empty] | 0 | 4007370.0493
Assets impairment | [7 empty] | 0 | [6 empty] | 0
Finance charges | 574369.152 | 47864.096 | 47864.096 | 47864.096 | 47864.096 | 47864.096 | 47864.096 | 47864.096 | 47864.096 | 47864.096 | 47864.096 | 47864.096 | 47864.096 | 574369.152 | 0
Repairs and Maintenance | 0 | [6 empty] | 0 | [6 empty] | 0
Fresh Produce Market Operations | 2743144.159 | 362789.3125 | 271357.65 | 276357.65 | 356276.41 | 271357.65 | 281607.63 | 368268.75 | 137345.7488 | 142345.7488 | 152789.3088 | 70729.57 | 51918.73 | 2743144.159 | 0 | 0 | -139489.3412
Abattoir Operations | 17627160 | 2241901.5395 | 1960604.9295 | 1307749.3555 | 1388809.56 | 1326379.13 | 881362.47 | 1871457.89 | 1705707.71 | 1740662.26 | 1139670.2925 | 1073490.8325 | 989364.3816 | 17627160.3511 | -0.35112
Dairy Farm Operations | [14 empty] | 0
Farms Operations | 4848096.8083 | 144116.84 | 249756.53 | 1227443.7 | 665803.81 | 268755.01 | 220774.93 | 306738.44 | 139420.25 | 1201081.32 | 132193.3322 | 166306.34 | 125706.05 | 4848096.5522 | 0.25611
Water Services Operations | [14 empty] | 0
Special Projects (Transfers and Grants) | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 |  | 0
Other Operating Expenditure | 8160525.9855 | 329391.996 | 379130.016 | 1033331.106 | 1021105.916 | 1748186.046 | 577026.786 | 596365.416 | 460231.326 | 610414.686 | 462568.8104 | 468154.4404 | 474619.1004 | 8160525.6453 | 0.34017
Adjustments to Biological Assets | 105000 | [6 empty] | 0
Total Expenditure | 84080620.6292 | 7045906.3873 | 6492383.5644 | 7481921.2504 | 7083530.1349 | 9223100.5291 | 5592306.2549 |  | 6390411.728 | 7326038.4537 | 5538756.1829 | 5726387.8761 | 5273142.7009 | 79968249.9973
Capital Expenditure | 982268 |  |  | 132268 |  |  | 400000 |  |  | 150000 |  |  | 300000 | 982268
1266689.9317